## Sheet1
Bond Details |  | WIP Details | NASBP Details
Contract / Project #: | → | Contract # |  | Job Number
Legal Project Name: | → | Contract Name |  | Job Name
Bond # | → | Bond # |  | --
Contract Price | → | Total Contract Price |  | Contract Price including Change Orders | Default Input from Active Bond
|  | Billings to Date |  | Billed To Date | Input Field :: Currently, how much you have billed the client ?
|  | Total Estimated Costs |  | Estimated Total Cost | Sum of Billed To Date and Estimated Cost to Complete (G9 + G15)
|  | Current Costs to Date |  | Cost to Date | Input Field :: How much spent till date on a Project
| Totals | Gross Profit (Loss) |  | Estimated Gross Profit | Difference between Contract Price - Estimated Total Cost (G6 - G8)
Gross Profit (Loss %)
| Progress To Date | Contract Revenues |  | Revenue Earned to Date | Cost to Bill based on Contract Price * Percent of Project Complete (G6 * G14)
|  | Gross Profit (Loss) |  | Earned Profit to Date | Profit made based on Revenue Earned * Percent of Project Complete (G12 * G14)
|  | Percent Complete |  | Estimated Percent Complete | Percentage of Cost to Date w.r.t Estimated Total Cost ((D9*100)/D8)
|  | Estimated Costs to Complete |  | Estimated Cost to Complete | Input Field :: Estimate How much more to spend in order to complete the project
|  | Under Billings |  | Costs & Est. Earnings > Billings
|  | (Over) Billings |  | Billings > Costs & Est. Earnings
Provision for Loss
| Prior Year | Revenues Earned |  | Revenue
|  | Cost of Revenues |  | Cost
|  | Gross Profit (Loss) |  | Gross Earnings
| Current Year | Revenues Earned |  | Revenue Earned
|  | Contract Costs |  | Cost of Construction
|  | Gross Profit (Loss) |  | Gross Earnings
Gross Profit (Loss %)
| Future |  |  | Remaining Revenue
Estimated Cost to Complete
Estimated Gross Earnings